## Report 1 - Mock-up
Open Recommendations - (=filter applied in 'overseen party' field; if no filter applied=MENA Region)
OIOS AR2016/131/02 Issue Date: 05/12/2016. Iraq Iraq - Central and Southern Response Deadline: 30/04/2017
| Rec No | Recommendation | Criticality | Action Required | MENA Response | Planned Implementation Date | Title of Responsible Staff
| 1 | The UNHCR Representation in Iraq should develop and implement an action plan and dedicate sufficient resources to: (i) ensure alignment of its contingency plan and business continuity plan with its critical programme activities; (ii) undertake regular reviews of these plans, as well as simulation exercises, to assess the adequacy of their comprehensiveness and readiness for emergency response; and (iii) ensure that minimum contingency stocks are maintained. | Important | Submission to OIOS of: (i) evidence that the contingency plan and the business continuity plan are aligned with critical programme activities; (ii) evidence that these plans are reviewed regularly; and (iii) MSRP stock reports in support of the contingency stock maintained. Recommendation 1 remains open pending receipt of: (i) an action plan developed to ensure that the contingency plan and business continuity plan are aligned with critical programme activities; (ii) evidence of institutional arrangements established for review of these plans; and (iii) MSRP stock reports in support of the contingency stock maintained." | The Representation accepted recommendation 1 and stated that it: (i) would continue its efforts to ensure the alignment of contingency and business continuity plans with critical programme activities, and to assess their comprehensiveness and readiness for emergency response; and (ii) was now maintaining a minimum contingency stock. The Representation accepted recommendation 1 and stated that it: (i) would continue its efforts to ensure the alignment of contingency and business continuity plans with critical programme activities, and to assess their comprehensiveness and readiness for emergency response; and (ii) was now maintaining a minimum contingency stock. | 2017-03-31 | Deputy Representative
| 2 | The UNHCR Representation in Iraq should develop and implement an action plan and dedicate sufficient resources to: (i) ensure alignment of its contingency plan and business continuity plan with its critical programme activities; (ii) undertake regular reviews of these plans, as well as simulation exercises, to assess the adequacy of their comprehensiveness and readiness for emergency response; and (iii) ensure that minimum contingency stocks are maintained. | Important | Submission to OIOS of: (i) evidence that the contingency plan and the business continuity plan are aligned with critical programme activities; (ii) evidence that these plans are reviewed regularly; and (iii) MSRP stock reports in support of the contingency stock maintained. Recommendation 1 remains open pending receipt of: (i) an action plan developed to ensure that the contingency plan and business continuity plan are aligned with critical programme activities; (ii) evidence of institutional arrangements established for review of these plans; and (iii) MSRP stock reports in support of the contingency stock maintained." | The Representation accepted recommendation 1 and stated that it: (i) would continue its efforts to ensure the alignment of contingency and business continuity plans with critical programme activities, and to assess their comprehensiveness and readiness for emergency response; and (ii) was now maintaining a minimum contingency stock. The Representation accepted recommendation 1 and stated that it: (i) would continue its efforts to ensure the alignment of contingency and business continuity plans with critical programme activities, and to assess their comprehensiveness and readiness for emergency response; and (ii) was now maintaining a minimum contingency stock. | 2017-03-31 | Deputy Representative
IGO INS/16/03 Issue Date: 10/11/2016 Iraq Response Deadline:
| Rec No | Recommendation | Criticality | Action Required | MENA Response | Planned Implementation Date | Title of Responsible Staff
| 1 | (Medium) - The FSA should monitor managers’ accountability for assuring respect for and understanding of applicable security SoPs and the Security Risk Management process (SRM) including most recent9 by all staff. | Not Applicable
Filters Applied: Implementation Status=Open, Overseen party=Iraq
Run Date: 03/11/2017